# MapAble – Brandon Cooper

## 🚀 Launchpad (At-a-Glance)

Mission (30 days): Establish MapAble’s identity spine and SSO so all future features inherit security, consent, and accessibility by default.

North Star Outcomes: - One login across MapAble, Australian Disapedia, and AccessiBooks - Canonical profile + roles + consent enforced server-side - Audit trail for all identity actions - Skeleton unified calendar ready for next phase

Success = boring auth, predictable sessions, zero surprises.

Non‑Negotiables: - Server-validated auth only (no client trust) - Explicit consent gates for every integration - Accessibility is a build constraint - Document decisions as you go

Do First (Week 1): - Get Preview deployments green on Vercel - Supabase connected with RLS enabled - /api/me returns profile, roles, consents

Do Not Build Yet: payments, ads, full bookings, accreditation engines, org hierarchies.

Escalate Immediately If: consent enforcement is unclear, MediaWiki/OIDC mapping conflicts, or sessions behave inconsistently across SSR/refresh.

## 🎯 Definition of Done – Task Tracker (Applies to ALL work)

A task is NOT done unless all applicable criteria below are met. This is a quality gate, not a suggestion.

### 1. Security & Identity

- Auth is server-validated (no trusting client state)

- Sessions survive refresh and SSR transitions

- Secrets stored only in env vars (never committed)

- No hard-coded IDs, tokens, or test bypasses

### 2. Consent & Privacy

- Any cross-system action is gated by an explicit consent check

- Consent revocation takes effect immediately (no stale sessions)

- Only minimum required data is shared (data minimisation)

### 3. Access Control (RLS & Roles)

- Row-Level Security prevents cross-user access

- Role checks enforced server-side

- No reliance on UI-only permission checks

### 4. Audit & Traceability

- Auth events logged (login, logout, link, unlink)

- Consent changes logged

- Integration log entries are human-readable

### 5. Accessibility (Baseline)

- Fully keyboard navigable

- Screen reader labels present and meaningful

- No time-based traps or motion-only cues

### 6. Reliability & DX

- Feature works on Preview deployment

- CI passes (lint, typecheck, tests)

- Setup or usage documented in README if non-obvious

### 7. Demo-ability

- Can be demonstrated in under 2 minutes

- Failure modes can be explained

If any box is unchecked, the task remains IN PROGRESS.

## ✅ Week-by-Week Checklist (Tick-off)

### Week 1 – Foundations (repo, deploy, env)

- Canonical repo confirmed (Cursor version) and Replit is non-prod

  - Confirm Cursor repo URL + default branch

  - Confirm Replit is prototype only; add banner note in Replit README

  - Create repo CODEOWNERS (Brandon + Jonathan)

  - Add .gitignore sanity check (env files excluded)

- Branch protections enabled (PR required into main)

  - Require PR approvals (min 1)

  - Require status checks (lint/typecheck/tests)

  - Disable force-push to main

  - Enable signed commits (optional)

- Local dev runs on a clean machine (dev command documented)

  - Pin Node version (e.g., .nvmrc or engines)

  - Confirm package manager + lockfile committed

  - Verify npm/pnpm/yarn run dev boots without manual steps

  - Document prerequisites (Node, Git, Supabase CLI optional)

- Vercel project connected to repo with Preview deployments on PR

  - Import repo into Vercel (correct root directory)

  - Confirm framework detection (Next.js)

  - Enable preview URLs per PR

  - Add preview protection (optional) if sensitive

- Environments created: Preview + Production

  - Create Preview env var set

  - Create Production env var set

  - Confirm no secrets appear in client-exposed vars

- .env.example created (no secrets)

  - List required env vars with descriptions

  - Mark server-only vars clearly

  - Include sample placeholders

- Supabase dev project confirmed/created

  - Confirm project region (prefer AU)

  - Confirm database password stored securely

  - Confirm API URL and anon key available

- Vercel env vars set for Preview (Supabase URL/Anon key + server-only keys)

  - Add NEXT_PUBLIC_SUPABASE_URL

  - Add NEXT_PUBLIC_SUPABASE_ANON_KEY

  - Add server-only SUPABASE_SERVICE_ROLE_KEY (Preview)

  - Add NEXTAUTH_SECRET (or equivalent) if used

- First “green” Preview deployment verified

  - Open preview URL and verify homepage renders

  - Confirm server routes respond (health check)

  - Confirm no build warnings related to env vars

- README updated: run, test, deploy, env var list

  - Add “Local Setup” section

  - Add “Deployment (Vercel)” section

  - Add “Environment Variables” section

  - Add “Troubleshooting” section

### Week 2 – Auth Spine (sessions, profiles, RLS)

- Supabase SSR auth wired (server client, browser client, middleware refresh)

  - Create supabase/server.ts helper (SSR cookies)

  - Create supabase/client.ts helper (browser)

  - Add middleware.ts session refresh and route gating

  - Confirm session survives refresh + SSR navigation

- Protected route added (/app or equivalent)

  - Define protected route group (e.g., /app/*)

  - Redirect unauthenticated users to /login

  - Add “returnTo” redirect after login

- Tables created: profiles, role_bindings, consents, audit_log

  - Write SQL migration(s) in repo

  - Apply to Supabase dev DB

  - Add indexes on user_id and frequently queried fields

- RLS policies implemented and tested (cross-user access blocked)

  - Enable RLS on all user tables

  - Policies: users can read/write own profile

  - Policies: users can read/write own consents

  - Add negative tests (cannot read another user)

- Profile bootstrap on first login (profile row auto-created)

  - Create upsert on login callback / server route

  - Ensure idempotent (safe to call multiple times)

  - Backfill script (optional) for existing users

- Consent UI stub created (Disapedia + AccessiBooks toggles)

  - UI: settings page with two toggles

  - API: update consent endpoint (server validated)

  - Display “effective immediately” message

- GET /api/me implemented (server-validated) returning profile + roles + consents

  - Route handler validates session

  - Fetch profile + roles + consents in one query where possible

  - Return minimal safe payload (no secrets)

- Audit events written for login/logout/consent change

  - Define audit event schema + enums

  - Write log events in server routes

  - Confirm logs are queryable for debugging

- Basic auth regression tests added

  - Login flow test (happy path)

  - Refresh/session persistence test

  - RLS negative test

### Week 3 – Federation: Disapedia (VentraIP MediaWiki)

- Supabase OIDC issuer enabled (or equivalent auth issuer configured)

  - Confirm issuer URL / discovery endpoint

  - Confirm scopes supported: openid email profile

  - Decide canonical identifier strategy (sub + verified email)

- OIDC client created: disapedia (redirect URI confirmed)

  - Confirm Disapedia callback URL (Special:PluggableAuthLogin)

  - Register redirect URI exactly (no wildcards)

  - Store client secret securely (VentraIP config)

- MediaWiki extensions installed: PluggableAuth + OpenID Connect

  - Confirm compatible MediaWiki version

  - Install extensions under /extensions

  - Enable in LocalSettings.php

- LocalSettings.php configured with issuer + client ID/secret

  - Configure provider URL / endpoints

  - Set username mapping rule (email vs derived)

  - Configure auto-provision on first login

  - Set logout behavior (optional: global logout)

- First successful Disapedia login via “Login with MapAble”

  - Test first-time user provisioning

  - Test returning user login

  - Test failed login path and error messaging

- Account auto-provisioning rules confirmed (email vs derived username)

  - Confirm collision handling

  - Confirm display name policy

  - Confirm whether email is shown publicly or not

- Consent gate enforced (revoked consent blocks new sessions)

  - Implement MapAble-side consent check before initiating OIDC

  - Define expected behavior on revoke (block re-auth + prompt)

  - Add UI explanation in MapAble settings

- Audit log captures: Disapedia link/unlink and login attempts

  - Log LINK_DISAPEDIA on first successful SSO

  - Log UNLINK_DISAPEDIA on revoke

  - Log failed attempts (rate-limited)

### Week 4 – Federation: AccessiBooks (Replit) + Core stub

- AccessiBooks framework confirmed and callback URL fixed

  - Identify runtime (Express/Next/Remix/etc.)

  - Confirm public base URL (production/staging)

  - Define callback route: /auth/callback (or equivalent)

  - Confirm HTTPS and cookie domain behavior on Replit

- OIDC client created: accessibooks (PKCE flow)

  - Register exact redirect URI

  - Confirm PKCE required and supported

  - Store client secret safely (server-side only)

- “Login with MapAble” implemented in AccessiBooks (auth code + PKCE)

  - Generate verifier/challenge

  - Redirect to authorize endpoint with scopes

  - Exchange code for tokens server-side

  - Validate ID token signature and nonce

- Server-side session storage implemented (secure cookies)

  - HttpOnly + Secure + SameSite set appropriately

  - Session rotation on login

  - Logout clears session and tokens

- external_linkages table added and populated on first login

  - Table migration added + applied

  - Link record created on first successful SSO

  - Idempotent linking (no duplicates)

- Consent gate enforced for AccessiBooks (revoked blocks re-auth)

  - MapAble consent toggle in settings (already stubbed)

  - AccessiBooks checks consent on auth start or token exchange

  - Revoke path documented for users

- Minimal calendar schema created: calendar_events

  - SQL migration created + applied

  - RLS policy: user can access own events

  - Index on user_id and start_at

- Read-only “Today” view shows events (even seeded data is OK)

  - Server route fetches today’s events (timezone-safe)

  - UI list renders with accessible labels

  - Empty state message (accessible)

- CI checks added (lint + typecheck + tests) and passing

  - Configure GitHub Actions (or equivalent)

  - Run lint, typecheck, unit tests

  - Block merge on CI failure

- End-of-month demo script written (3 logins + /me + calendar stub)

  - Demo: MapAble login + /api/me

  - Demo: Disapedia login via MapAble

  - Demo: AccessiBooks login via MapAble

  - Demo: Calendar “Today” view

# MapAble – Brandon Cooper

## First 30 Days Task List + “What Not to Build Yet” + SOW Appendix + Executive Cover Note

Prepared for: Brandon Cooper (Developer)

Prepared by: Jonathan Shar

Context: This document is an add-on to the main “MapAble Developer Briefing”. It provides (1) an execution-ready first-30-days plan, (2) scope guardrails, (3) contract/SOW appendix language, and (4) a one-page cover note that Jonathan can send with the briefing.

# A) First 30 Days Task List (Brandon)

## Day 1–3: Environment, repo, and deployment sanity

Goal: You can run MapAble locally, deploy to Vercel Preview, and see a working auth session.

### Tasks

- Repo & branching

  - Confirm canonical repo (Cursor-engineered code) is the single source of truth.

  - Create branches: develop (optional), main protected, PR required.

  - Add CODEOWNERS (if using GitHub).

- Local dev setup

  - Confirm Node version and package manager (pnpm/yarn/npm).

  - Ensure npm run dev (or equivalent) works on a clean machine.

  - Document setup in README.md.

- Vercel projects

  - Configure Preview deployments from PRs.

  - Create environments:

    - Preview (staging-like)

    - Production

  - Ensure .env.example exists (no secrets).

- Supabase connection

  - Create/confirm a Supabase project for dev.

  - Add env vars to Vercel and local:

    - NEXT_PUBLIC_SUPABASE_URL

    - NEXT_PUBLIC_SUPABASE_ANON_KEY

    - SUPABASE_SERVICE_ROLE_KEY (server only)

### Acceptance criteria

- Preview deployment is automatic on PR.

- App boots locally with no manual hacks.

- Supabase connection works from server routes.

## Day 4–10: Authentication spine (MapAble)

Goal: A user can sign in, session persists with SSR cookies, and /me returns the canonical profile.

### Tasks

- Next.js App Router auth (SSR cookies)

  - Implement Supabase SSR client pattern:

    - server client helper

    - browser client helper

    - middleware.ts session refresh

  - Add protected route example: /app requires auth.

- Schema: profiles + roles + consents + audit_log

  - Create tables:

    - profiles (id uuid pk, display_name, prefs jsonb, created_at, updated_at)

    - role_bindings (user_id, role, scope, created_at)

    - consents (user_id, target_system, scope, granted boolean, updated_at)

    - audit_log (id, actor_user_id, action, target_type, target_id, metadata jsonb, created_at)

- Row-Level Security (RLS)

  - Users can read/write their own profile.

  - Users can read their own consent records.

  - Only privileged roles can read other users.

- Auth hook / bootstrap

  - On first login, ensure profiles row exists.

  - Write audit_log events for:

    - login

    - logout

    - consent change

- API

  - Add GET /api/me (server-validated) returning:

    - user id

    - profile

    - roles

    - consent summaries

### Acceptance criteria

- Login works end-to-end on Vercel Preview.

- Refreshing the page preserves session.

- /api/me returns profile + roles.

- RLS prevents cross-user access.

## Day 11–18: Federation (SSO) planning + Disapedia setup (VentraIP)

Goal: Disapedia can authenticate users via “Login with MapAble” using OIDC.

### Tasks

- OIDC issuer enablement (Supabase)

  - Enable Supabase OAuth/OIDC issuer.

  - Create OIDC client: disapedia.

  - Decide claims mapping: use stable sub + verified email.

- Disapedia (MediaWiki on VentraIP)

  - Install/enable:

    - PluggableAuth

    - OpenID Connect extension

  - Configure LocalSettings.php to point to the Supabase issuer, client id/secret, and redirect URI.

- Account provisioning rules

  - Confirm whether Disapedia usernames are:

    - email-based (simpler), or

    - derived (display name + suffix)

  - Confirm whether to auto-create accounts on first login.

- Audit & consent alignment

  - Add consent toggle in MapAble:

    - “Allow Disapedia login via MapAble”

  - If consent is revoked, disallow new sessions.

### Acceptance criteria

- Disapedia login redirects to MapAble login and returns successfully.

- Disapedia creates/links an account on first login.

- Consent toggle exists and is enforced.

## Day 19–26: AccessiBooks SSO (Replit) and linkage table

Goal: AccessiBooks accepts “Login with MapAble” via OIDC, links users by sub, and stores a safe session.

### Tasks

- Confirm AccessiBooks runtime

  - Identify framework (Express/Next/Remix/etc.).

  - Identify public base URL and callback route.

- OIDC client: accessibooks

  - Create OIDC client entry for AccessiBooks.

  - Implement OAuth Authorization Code + PKCE.

- Session security

  - Store session server-side (cookie-based preferred).

  - Do not store secrets in client.

- Linkage storage in MapAble

  - Add external_linkages table:

    - user_id

    - system (accessibooks/disapedia)

    - external_subject (sub or system user id)

    - linked_at

- Consent enforcement

  - MapAble consent toggle gates the ability to log in to AccessiBooks.

### Acceptance criteria

- AccessiBooks can authenticate via MapAble.

- Users are linked consistently by stable identifier.

- Consent revocation blocks re-auth.

## Day 27–30: Core skeleton for next phase (calendar model + operating discipline)

Goal: Prepare the next month without scope creep.

### Tasks

- Unified calendar schema (skeleton only)

  - Create calendar_events table:

    - id, user_id, type, start_at, end_at, title, metadata jsonb, created_at

  - Add one simple UI view: “Today” list (read-only is fine).

- Engineering hygiene

  - Add lint + typecheck + basic tests to CI.

  - Add secret scanning if possible.

  - Add structured logging for auth and critical endpoints.

- Documentation

  - Update README with:

    - env vars

    - how to run

    - how to deploy

    - known constraints

### Acceptance criteria

- Calendar events table exists and can be read.

- CI blocks obvious breakages.

- Core docs are usable by a new dev.

# B) “What Not to Build Yet” (Scope Guardrails)

These are explicitly out of scope for the first 30 days to protect quality and reduce rework.

## 1) No feature-heavy Care/Transport/Jobs builds yet

- No full booking engines

- No payment flows

- No complex rostering

Reason: Identity + consent + audit must be stable first.

## 2) No monetisation surfaces

- No sponsored placements

- No ad decisioning

- No advertiser dashboards

Reason: Monetisation without trust primitives creates reputational risk.

## 3) No “deep” accessibility accreditation engine

- No full scoring rubric implementation

- No evidence upload workflows

Reason: Needs stable data model and operational process design.

## 4) No multi-tenant provider org management

- No provider hierarchies

- No staff management panels

Reason: Roles/permissions must be proven in simpler mode first.

## 5) No premature microservices

- Keep a modular monolith approach in this phase.

Reason: Early splitting increases complexity and slows delivery.

## 6) No long-lived sensitive data sync

- Avoid pushing disability-related profile data to partner systems.

Reason: Consent language and data minimisation need careful work.

# C) Contract / Statement of Work Appendix (Copy/Paste)

Appendix X: Development Scope, Deliverables, and Acceptance Criteria (First 30 Days)

## 1. Scope

The Developer will implement MapAble’s foundational identity and integration layer including Supabase authentication, server-validated sessions, a canonical user profile model, role/consent storage with enforcement, audit logging, and single sign-on integration with (a) Australian Disapedia (MediaWiki hosted on VentraIP) and (b) AccessiBooks (application hosted on Replit).

## 2. Deliverables

- Authentication implementation for MapAble (Next.js App Router) using Supabase, including SSR cookie-based sessions and middleware session refresh.

- Database schema and RLS policies for profiles, role_bindings, consents, and audit_log tables.

- API endpoint GET /api/me returning authenticated user profile, roles, and consent summary.

- OIDC client configuration in Supabase for Disapedia and AccessiBooks.

- Disapedia OIDC integration using MediaWiki extensions (PluggableAuth + OpenID Connect), configured to authenticate via MapAble.

- AccessiBooks OIDC integration implementing OAuth Authorization Code + PKCE, establishing sessions and mapping users to a stable identifier.

- External linkage table connecting MapAble users to partner system subjects/IDs.

- Core skeleton: creation of a minimal calendar_events table and a read-only “Today” view.

- Developer documentation for local setup, environment variables, and deployment workflow.

## 3. Out-of-scope (explicit exclusions)

The following are excluded unless a written variation is agreed: - Full Care/Transport/Jobs booking workflows - Payments and billing processing - Advertising/monetisation features - Full accreditation scoring engine and evidence workflows - Multi-tenant provider organisation management - Sensitive data synchronisation beyond identity claims (email/sub)

## 4. Acceptance Criteria

The work will be accepted when: - MapAble supports sign-in/sign-out with persistent SSR sessions on Vercel Preview. - RLS prevents cross-user access to profile and consent data. - /api/me returns profile + roles + consent summary for authenticated users. - Disapedia users can authenticate via “Login with MapAble” successfully. - AccessiBooks users can authenticate via “Login with MapAble” successfully. - Consent revocation blocks re-auth for the associated partner system. - Audit logs record authentication events and consent changes. - Setup documentation enables another developer to run the project locally and deploy via Vercel.

## 5. Timeline

Target completion: within 30 calendar days from commencement, subject to timely provision of required credentials and domain access.

## 6. Assumptions and Client Responsibilities

Jonathan Shar (Client) will provide: - Access to relevant Vercel projects, domains/DNS settings, Supabase project, and Disapedia/AccessiBooks administration access. - Non-secret environment variable names and required callback URLs. - Timely review and sign-off on consent wording and role definitions.

# D) One-Page Executive Cover Note (Sendable)

Subject: MapAble Development Briefing and 30-Day Delivery Plan

Hi Brandon,

Thanks again for partnering on MapAble. I’m sending you the attached developer briefing and an addendum with a first-30-days plan.

MapAble is being built as a trust-first disability platform. The key early work is to establish a stable “identity spine” and integration layer so that MapAble, Australian Disapedia (MediaWiki), and AccessiBooks can share one secure login, governed by explicit user consent.

For the first 30 days, success means: - Supabase auth working in Next.js with server-validated SSR sessions - Canonical user profiles, roles, consents, and audit logs implemented with RLS - OIDC login working for Disapedia and AccessiBooks - A minimal unified calendar schema stubbed (read-only is fine)

I’ve also included a “what not to build yet” section to protect scope and avoid rework. We’ll layer Care/Transport/Jobs once the identity, consent, and audit foundations are solid.

If anything in the plan conflicts with what you see in the codebase, flag it early. I’d rather we slow down briefly than ship something we’ll need to unwind later.

Appreciate you bringing your skill to something that will materially improve access and participation.

Best, Jonathan Shar